## K01 submission
Reverse Timeline for K01 Submission
Task | Date
Alert grants office and colleagues | Fifteen weeks before due date
Identify program announcement | Fifteen weeks before due date
Process ideas with mentors and colleagues | Fifteen weeks before due date
Identify program officer | Fourteen weeks before due date
Identify responsibilities and team-members for submission | Fourteen weeks before due date
Draft aims | Fourteen weeks before due date
Circulate aims to colleagues | Thirteen weeks before due date
Meet with statistician | Thirteen weeks before due date
Draft significance and innovation | Twelve weeks before due date
Draft preliminary studies | Twelve weeks before due date
Revise aims | Twelve weeks before due date
Send aims to PO | Eleven weeks before due date
Draft budget | Eleven weeks before due date
Meet with primary mentors | Eleven weeks before due date
Assemble key personnel | Ten weeks before due date
Get bioskethces and other support | Nine weeks before due date
Draft research strategy | Nine weeks before due date
Get mentor and collaborator feedback | Seven weeks before due date
Draft training plan | Nine weeks before due date
Get mentor and collaborator feedback | Seven weeks before due date
Draft abstract, title page, and budget justifiation | Six weeks before due date
Finalize budget and justification | Six weeks before due date
Draft ancillary grant docs | Six weeks before due date
Finalize aims | Five weeks before due date
Revise ancillary grant docs | Four weeks before due date
Finalize training plan | Three weeks before due date
Finalize research strategy | Three weeks before due date
Send all documents to grants office | Three weeks before due date
Submit to sponsored programs | Two weeks before due date
Confirm documents in eRA Commons | two days before due date
Confirm submission with PO | due date

## R01 submission
Reverse timeline for R01 Grant Submission
Task | Date
Alert grants office and colleagues | Fifteen weeks before due date
Identify program announcement | Fifteen weeks before due date
Process ideas with mentors and colleagues | Fifteen weeks before due date
Identify program officer | Fourteen weeks before due date
Identify responsibilities and team-members for submission | Fourteen weeks before due date
Draft aims | Fourteen weeks before due date
Circulate aims to colleagues | Thirteen weeks before due date
Meet with statistician | Thirteen weeks before due date
Draft significance and innovation | Twelve weeks before due date
Draft preliminary studies | Twelve weeks before due date
Revise aims | Twelve weeks before due date
Send aims to PO | Eleven weeks before due date
Draft budget | Eleven weeks before due date
Assemble key personnel | Ten weeks before due date
Get bioskethces and other support | Nine weeks before due date
Draft research strategy | Nine weeks before due date
Get mentor and collaborator feedback | Seven weeks before due date
Draft abstract, title page, and budget justifiation | Six weeks before due date
Finalize budget and justification | Six weeks before due date
Draft ancillary grant docs | Six weeks before due date
Finalize aims | Five weeks before due date
Revise ancillary grant docs | Four weeks before due date
Finalize research strategy | Three weeks before due date
Send all documents to grants office | Three weeks before due date
Submit to sponsored programs | Two weeks before due date
Confirm documents in eRA Commons | two days before due date
Confirm submission with PO | due date

## Manuscript submission
reverse timeline for manuscript submission
Task | Date
Outline paper | Ten weeks before due date
Write summary of findings | Ten weeks before due date
Write first paragraph of introduction | Nine weeks before due date
Write last pargraph of introduction ("Current Study" paragraph) | Nine weeks before due date
Write middle of introduction | Nine weeks before due date
Send drafted introduction to content mentor/colleague | Eight weeks before due date
Write participants section | Eight weeks before due date
Write procedures section | Eight weeks before due date
Write measures section | Eight weeks before due date
Send drafted methods section to lead study coordinator | Seven weeks before due date
Write analysis plan section | Seven weeks before due date
Write results for hypothesis 1 | Seven weeks before due date
Write results for hypothesis 2 | Seven weeks before due date
Make tables and figures | Seven weeks before due date
Send drafted results section to statisitican | Six weeks before due date
Write first paragraph of discussion ("Current study" paragraph) | Six weeks before due date
Write last paragraph of discussion ("Conclusions" paragraph) | Six weeks before due date
Write limitations paragraph | Six weeks before due date
Write rest of discussion | Six weeks before due date
Write abstract | Six weeks before due date
Revise paper and tables and figures based on feedback from three colleagues | Five weeks before due date
Add references | Five weeks before due date
Send complete draft to all colleagues | Five weeks before due date
Revise based on colleague feedback | Three weeks before due date
Send targeted questions to colleagues for additional review/clarification | Two weeks before due date
Finalize manuscript | One week before due date
Submit | Due date